Theme/Sector: Water

SUMMARY WORKPLAN 2003

| # EVENT/ACTIVITY | EVENT DATE* | RESPONSE DEADLINE* | NRCs expected input/ participation | EXPECTED OUTPUT/ DATE | RESPONSIBLE EEA PJM/ETC |
| --- | --- | --- | --- | --- | --- |
| Workshops |  |  |  |  |  |
| EEA-EIONET Workshop on developments in Eurowaternet and Indicator Core Set | 8-9 May (to be confirmed) | 11 April to confirm attendance | Participation of NRCs inland and marine waters | Workshop report and agreement for future activities | /Tim Lack (WRc) |
| IRF Follow-up meeting on fisheries indicators | To be arranged |  | Fisheries experts by invitation | Work shop report and revised fisheries indicators | /Anna Salama (ENEA) |
| Country visits/training |  |  |  |  |  |
| New member countries: Cyprus, Malta, Turkey. Country visits to explain EEA/ETC work and EWN guidelines to NRCs | To be arranged |  | NFP and NRCs, supply of data flows for inland and marine waters | Implemented EWN in those countries. Country reports | /Tim Lack (WRc) |
| Country visit to FR Yugoslavia and Albania and any other countries on request (max 6) | To be arranged |  | NFP and NRCs, supply of data flows for inland and marine waters | Implemented EWN in those countries. Country reports | /Tim Lack (WRc) |
| # Data update requests/questionnaires # (including data flow obligations) |  |  |  |  |  |
| Eurowaternet priority dataflows - annual update | Sept-Dec 2003 | Sept-Dec 2003 | NRCs inland and marine waters data flows | Updated Waterbase, Updated indicator factsheets | /S. Nixon (WRc); J. Bogestrand (NERI), J. Grath (AWW), K Nygaard (NIVA) |
| EWN biological and hydromorphological data | Mar-May 2003 | Mar-May 2003 | Selected countries only – NRCs holding freshwater and marine data | Developing and testing indicators in preparation for WFD | /S. Nixon (WRc) |
| Draft reports for review |  |  |  |  |  |
| (From 2002 subvention) |  |  |  |  |  |
| Hazardous substances in Europe’s coastal waters | Q1 2003 | Q1 2003 | NRC haz.subs. | Final version | /N. Green (NIVA) |
| Water Indicator Report (including fact sheets) | Q1 2003 | Q1 2003 | NRCs inland and marine waters | Final version | /S. Nixon (WRc) |
| Report on IEA for water (part of the SOER 2004/5) | June 2003 | Aug 2003 | NFP/NRC IEA to review | Final version | Steve Nixon (ETC) |
| (From 2003 subvention) |  |  |  |  |  |
| Draft text for new ESR | ?? | ?? | NFP/NRC to review | Final version new ESR | /S. Nixon (WRc) |
| Revised Eurowaternet Guidelines | July 2003 | Sep 2003 | NFP/NRC to review | Final version revised guidelines | /S. Nixon (WRc) |
| Topic Report on fisheries and aquaculture | June 2003 | Aug 2004 | NFP/NRC to review | Final version of report | /A. Zenetos (NCMR) |
| Fact sheets for update/review |  |  |  |  |  |
| Water and fisheries core sets factsheets | May 2003 | July 2003 | NFP/NRC to review | Validated fact sheets | /S. Nixon (WRc), A. Zenetos (NCMR) |
| Other activities/events |  |  |  |  |  |
| None foreseen |  |  |  |  |  |