## SLO
Prihodnost naših voda
Usklajevanja za Načrt upravljanja z vodami
| Aktivnost | Junij | Julij | Avgust | September | Oktober | November | December
Priprave | Povzetki strokovnih podlag za posamezna porečja
Oblikovanje gradiv za delavnice
Regionalne delavnice (v sodelovanju z moderatorjem) | Dogovori, priprave v sodelovanju s predstavniki lokalnih skupnosti in organizacij
Izvedba delavnice: Mura
Izvedba delavnice: Drava
Izvedba delavnice: zgornja Sava
Izvedba delavnice: srednja Sava
Izvedba delavnice: spodnja Sava
Izvedba delavnice: Soča
Izvedba delavnice: jadranske reke
Priprava zapisnikov delavnic, zbirna ureditev predlogov in povratna informacija udeležencem
Sektorska usklajevanja | Kmetijstvo (prva usklajevanja v teku; predvidena zaključna predstavitev sodelovanja)
Promet (prva usklajevanja v teku; predvidena zaključna predstavitev sodelovanja)
Energetika (v dogovoru; predvidena zaključna predstavitev sodelovanja)
Industrija (v dogovoru; predvidena zaključna predstavitev sodelovanja)
Zaključna konferenca | Prva
Druga
Končno poročilo | Objava poročila
Sprejemanje pobud/komentarjev
Novinarska konferenca

## ENG
Our water future
Harmonization for Slovenian Water Strategy
| Activity | June | July | August | September | October | November | December
Preparation | Expert summaries for rivers' basins | bar: June to July
Material for workshops | bar: June to July
Regional workshops (cooperation of moderator) | Coordination with local community representatives and regional organizations | bar: July to August
Workshop: Mura
Workshop: Drava
Workshop: upper part of river Sava
Workshop: middle part of river Sava
Workshop: lower part of river Sava
Workshop: Soča
Workshop: Adriatic rivers
Records, organizing comments, feedback for involved in workshops | bar: October
Involving different sectors | Agriculture (on-going cooperation; final presentation) | bar: June to August
Traffic (on-going cooperation; final presentation) | bar: June; October
Energy (preparation phase; final presentation) | bar: June to July; October
Industry (preparation phase; final presentation) | bar: June; October
Final conference | First | bar: November
Second | bar: November
Final report | Published final report | bar: November
Comments | bar: November
Press conference | bar: November